## Sheet1
Task ID | Activity | Actual Start Date | Actual Stop Date | Reinspection Date | Status | CSD Letter Sent | Notes | Results_Findings
19-27878 | CSD - Rental Certification Inspections | 2019-12-05 | 2020-01-30 | 2020-08-13 09:00 | Completed | NSD 01 - Notice and Order |  | * BETH AND I WILL BE PREFORMING THE HCI. TCH 1-30-2020 NOTIFIED RICH OSWALD OF THE SEVERITY OF THE VIOLATIONS AND THAT THERE IS A POSSIBILITY OF HAVING TO CLOSE THE BUILDING. RECVD VERBAL CONFIRMATION FROM OSWALD WHO SAID " I'M NOT AFRAID OF CLOSING THE BUILDING DOWN. GO AHEAD AND PROCEED". TCH * 6-30-2020 SENDING ORIGINAL N&O LETER WITH NEW RI DATE POST COVID. COPY SENT TO BOTH THE DH AND MGR. TCH
20-7839 | CSD - Reinspection - Housing | 2020-01-30 | 2020-08-27 | 2020-10-14 09:00 | Completed | NSD 01 - Notice and Order | * RI - NO STRUCTURAL REPORT , FIRE SYSTEM INSPECTED BUT BACK FLOW VALVE HASN'T BEEN INSPECTED SINCE 2017, WEST EXTERIOR WALL HASN'T BEEN ADDRESSED. TCH | * MET WITH MAINT. ARRON & MGR. GEORGE - NO STRUCTURAL ENGINEER REPORT, ROOF NOT FIXED, WEST WALL HAS NO REPAIRS DONE. INTERIOR VIOLATIONS STILL EXIST. RESENT STORM BLEW A FEW BRICK OFF THE SOUTHWEST CORNER OF THE BUILDING. * CALLED MGR GEORGE - DISCUSSION LEAD TO OWNER MARK ROEMER WASN'T ALLOWING MGR GEORGE TO GET BIDS FOR ROOF OR EXTERIOR WALL REPAIR NOR THE ENGINEERING REPORT. GEORGE STATED THAT EVERYTHING ELSE HE WAS ABLE TO DO REPAIRS EXCEPT THE BATH FANS SHIPMENT HASN'T ARRIVED. INFORMED GEORGE THAT WORK WILL NEED TO GET DONE AND IF NOT A MUNICIPAL CITATION WOULD BE WRITTEN TO MARK ROEMER TO SPARE THE TENANTS HAVING TO MOVE. TCH
20-62930 | CSD - Rental Property Complaint Inspection | 2020-09-16 | 2020-09-16 |  | Completed |  | CHRIS BERRY CLD IN HE IS FATHER OF DILLON BERRY WHO LIVES HERE, AT APT 210 CHRIS IS ALSO ON THE LEASE. ROOF HAS BEEN LEAKING-TARPS WERE PUT UP BUT STILL GETTING WATER IN KITCHEN OVER SINK AND STOVE AND CEILING TILES ARE FALLING CAUSING DEBRIS ALL OVER. THEY WERE TOLD PARTS WERE ORDERED BUT NO TIMELINE TO WHEN IT WOULD BE FIXED AND NOTHING ELSE DONE ON THE INTERIOR TO HELP WITH THIS. CHRIS NUMBER IS 419-306-1409 AND DILLONS NUMBER IS 419-788-4213 | * 9-16-2020 CALLED CHRIS (DAD/OHIO) AND LEFT MESSAGE ON VOICEMAIL. CALLED DILLON (TENANT) AND TALKED THROUGH HIS OPTIONS. DILLON RETRACTED HIS COMPLAINT FOR THE REASON OF NO RAIN IN THE FORECAST AND CONSTRUCTION ON THE ROOF HAS BEGUN. ALLIANCE CONTRACTING IS REPLACING THE (PERMITTED) ROOF AS OF 9-15-2020 WHICH SHOULD BE DONE WITHIN THE WEEK. TCH
20-58268 | CSD - Reinspection - Housing | 2020-08-26 | 2020-10-23 | 2020-12-01 10:00 | Completed | NSD 09-Official Notice-1st Reinspection | * FINAL RI X 78 UNITS. | * 8-18-2020 FIRE MARSHAL JIM MORRIS CONTACTED ME ABOUT EXTERIOR BRICKS FALLING ONTO SIDEWALK . MET WITH OWNER MARK ROEMER, FIRE MARSHAL JIM MORRIS, CHRIS BELSER- BI STATE MASONRY AND CHRIS TOWNSEND - TOWNSEND ENGINEERING. BLOCKED OFF SIDEWALKS AND CLOSEST TRAFFIC LANES ON W 4TH ST & MAIN ST. 8-18-2020 (AFTERNOON) CALLED BY CHRIS BELSER DUE TO WALL ABOVE 6TH FLOOR COMING LOOSE. CALLED OSWALD AND CLOSED MAIN STREET WITH MY TRUCK UNTIL ASSISTANCE ARRIVED. LOOSE BLOCKS WERE REMOVED AND WALL SECURED WITH LUMBER. TCH * 8-21-2020 DISCUSSION WITH MGR GEORGE - ROOF, WALL REPAIR OUT FOR BID VIA INSURANCE CLAIM. * 8-25-2020 CALLED CHRIS BELSER/BI STATE - ASKED FOR HIM TO REPLACE CITY BARRICADES WITH HIS OWN. EMAILED OSWALD AND DAY GUY OF CHANGE. TCH * 8-26-2020 RCVD EMAIL FROM DAN GUY LATE AFTERNOON STATING CITY'S BARRICADE WERE REMOVED WHILE "5 CONES WITH CAUTION TAPE ON SIDEWALK BY ENTRANCE." DOVE DOWN AND FOUND 5 CONES SPREAD OUT UNDER AFFECTED AREA ON MAIN ST. USED CONES WHAT THE CITY DID'T RETRIEVE AND EXPANDED AREA OUT TO ON STREET PARKING FROM 4TH STREET CORNER TO JUST SHORT OF THE MAIN STREET ENTRANCE. MET WITH DAVE/BI-STATE WHO STATED THE UPPER LEVEL EXISTING BRICK HAS BEEN SECURELY ANCHORED - THAT HAPPENED AFTER DAY OF SECURING AFFECTED AREA ON MAIN ST. EXPLAINED TO DAVE THE CAUTION TAPE WILL HAVE TO BE MONITORED BY BI-STATE . TCH * 9-28-2020 SENT COPY OF CURRENT N&O VIA EMAIL TO ANDREW WOLD DUE TO THE UNDERSTANDING THAT WOLD IS IN THE PROCESS OF PURCHASING THE PROPERTY. TCH * 10-13-2020 Called Mark Roemer who stated Alliance Construction bid out the work for the brick repair. Street sides to Bi-State and the west side to someone yet to be named. I called Bi-State and talked to Steve Belser to confirm and Chris stated that the contract will be signed today and the scaffolding will be installed today at the sidewalks. tch * 10-13-2020 RECVD A SIGNED CONTRACT FOR THE EXTERIOR BRICK WORK BY BI-STATE. WORK TO BEGIN SPRING 2021. TCH * 10-23-2020 FINAL SENT TO DH, MGR AND LAYWER. TCH
20-62291 | BUILDING PERMIT | 2020-09-11 | 2020-12-04 |  | Completed |  | COVER ROOF WITH 80 SQUARE OF EPDM. LAY OVER 1 LAYER OF EXISTING ROOF COVERING. 2 LAYERS MAX. OF SHINGLES, 1 LAYER OF BUILDUP- ICE SHIELD REQUIRED BY CODE.
20-82742 | CSD - Rental Property Complaint Inspection | 2020-12-17 | 2021-01-26 | 2021-01-18 09:01 | Completed | NSD 04 - Complaint Notice and Order | * TENANT DENA VOORHEES (309-203-3205) IN APT #311 - CALLED ABOUT WATER DAMAGED CEILING AND DAMAGED WINDOW. | * 1-13-2021 CALLED TENANT DENNA TO ASK IF REPAIRS HAD BEEN MADE. DENNA STATED THAT SHE DID'NT MIND ME NOT COMING BACK FOR RI DUE TO HER MOVING OUT 2-5-2021. WILL CALL 2-4-21 TO REVISIT COMPLAINT. TCH
20-72033 | CSD - Reinspection - Housing | 2020-11-18 | 2021-02-16 | 2021-05-14 10:00 | Completed | NSD 21 - Notice of Extension | * FINAL RI - INTERIOR | * 12-1-2020 RI - INTERIOR VIOLS SATISFIED IN OCCUPIED APARTMENTS AND COMMONS. EXTERIOR VIOLS EXIST WITH A MAY 14TH REVISIT. LACKING ENGINEER'S REPORT. WILL WAIT A FEW DAYS. TCH * 12-4-2020 DROVE BY WEST EXTERIOR WALL - NOTICED TWO HOLES AND ADDITIONAL DETERIORATION OF THE WALL. CHRIS/BI-STATE WAS CALLED AND HE AND CHRIS WITH TOWNSEND WILL INVESTIGATE. * 12-7-2020 PER TRISHNA ROOF REPLACEMENT IS COMPLETE AND PERMIT CLOSED. TCH 12-15-2020 DROVE BY WEST WALL AND NOTICED HOLES AND ADDITIONAL DETERIORATION OF THE WEST WALL. * 12-16-2020 CALLED CHRIS/BI-STATE - HE WAS TOLD THAT ANDREW WOLD WILL BE SECURING WEST WALL. CALLED CHRIS/TOWNSEND - CHRIS SAID HE WILL HAVE ENGINEER'S REPORT BY THE END OF TODAY. TCH * 1-11-2021 MET WITH TRISHNA & SETH (BRICK REPAIRMAN) AND DISCUSSED WHAT NEEDED TO CONTINUE FOR REQUIRED REPAIRS. ANDREW WOLD ARRIVED AFTER TRISHNA LEFT AND I REITERATED TO ANDREW THE REQUIREMENTS AND EXPLAINED TRISHNA WILL BE SENDING A FOLLOW UP EMAIL OF OUR DISCUSSION. TCH * 2-16-21 SENDING OUT EXTENSION LETTER FOR REMINDER OF WHAT WORK IS REQUIRED AND DATES REQUIRING EXTERIOR WORK TO HAVE BEGUN. LETTER SENT TO ROEMER/OWNER REGULAR AND EMAIL ALONG WITH MGR WILDWOOD PROPERTIES. TCH
21-30875 | Vehicle Tag - Nuisance | 2021-05-17 | 2021-05-25 |  | Completed |  | *7 day tag for tow* Black Chevy S10 Plate: IVU933 IA (8/2020) Violations: inoperable, lacks current registration, leaking flammable /hazardous fluid, partly dismantled, functioning as a solid waste container, cannot be legally operated on streets/highways, dangerous/defective, and nuisance complaint | Complaint: Multiple broken down vehicles in parking lot. Black Chevy pick up with flat tires, older chevy caprice with flat tires Two other vehicles tagged on parcel L007-28 5/17/21 stb There is currently a guy working on the truck. He said that the ball joint is supposed to come in tomorrow and then it will be drivable. I told him that i would come back tomorrow to check on it and that the bed of the truck should be cleaned out as well 5/24/21 stb Truck is gone 5/25/21 stb
21-9198 | CSD - Reinspection - Housing | 2021-05-14 | 2021-05-26 | 2021-07-15 09:00 | Completed | NSD 09-Official Notice-1st Reinspection | * RI - INTERIOR/EXTERIOR VIOLS. | 4/28/2021 emailed inspection report to Sara Tyler email and village property mgmt email -hb *5-14-2021 RI - FOUND WEST EXTERIOR WALL IN SEMI-COMPLETED FORM WITH SCATERED UNGROUTED AREAS PAINTED OVER. APT #417 OCCUPIED (VAC/SS), SEVERAL SMOKE DETECTORS MISSING IN VACANT APTS, NO WORK DONE. BILLING FOR RI FEE AND PF'S. FINAL SENT WITH NEW VIOLS. TCH * 5-24-21 CALL WITH JIM BACCI (?) 515-281-5415 WITH STATE OF IA ELEVATOR/ESCALATOR DIV - BOTH ELEVATORS HAVE HAD FAILED INSPECTION IN 1-20-20. THE STATE HAS TRIED AND HAVEN'T BEEN ABLE TO CONTACT OWNER OR GET VARIFICATION OF INSPECTION COMPLIANCE. PROPERTY, PER JIM MATTER WAS TURNED OVER TO STATE LEGAL BUT NOT FOLLOWED UP ON. GAVE JIM CONTACT INFO FOR DH AND ASKED FOR FOLLOW UP CALL IF ANY ACTION. TCH * 5-26-21 MAILED AND EMAILED COPY OF FINAL N&O TO ROEMER, CC'D EMAIL TO VILLAGE PROPS (SARAH) AND ALLIED (KYLE). TCHJ
21-38330 | CSD - Vehicle Issue | 2021-06-18 | 2021-06-18 |  | Completed |  | Multiple broken down vehicles, vehicles missing wheels in parking lot | All vehicles appear to be functional….and none of them have missing tires. Complaint unfounded 6/18/21 stb
21-42476 | CSD - Rental Property Complaint Inspection | 2021-07-15 | 2021-07-19 | 2021-08-23 10:00 | Completed | NSD 04 - Complaint Notice and Order | PATRICK BROWN FROM UNIT 105 CALLED IN 563-320-4410 - DRYWALL AROUND DOOR TO PARKING LOT IS NOT STABLE AND DOOR IS VERY DIFFICULT TO OPEN -NOT SURE IF STRUCTURALLY SOUND | 8 7-19-21 TALKED WITH TRISHNA AND AGREED A STRUCTURAL REPORT MUST BE OBTAINED FOR THE 1ST LEVEL WALL ALONG THE WEST SIDE. TCH
21-44091 | CSD - Rental Property Complaint Inspection | 2021-07-21 | 2021-07-21 | 2021-08-05 09:00 | Completed | NSD 04 - Complaint Notice and Order | DILLON BERRY UNIT 210 419-788-4213 - FATHER CHRIS WHO IS ON THE LEASE WITH HIS SON CLD IN ABOUT CEILING FALLING IN KITCHEN - TOILET ALSO LEAKING FROM THE HANDLE. HAVE TRIED CONTATING MGMT SINCE MONDAY BUT NO RESPONSE | * 8-5-21 RI - NEW LED HALL LIGHTS INSTALLED
21-7386 | ELECTRICAL PERMIT | 2021-02-04 | 2021-07-27 |  | Completed |  | INSTALL (4) CAN LIGHTS | passed final inspection 7/27/2021 11:34:37 AM
21-44867 | CSD - Reinspection - Housing | 2021-08-05 | 2021-08-10 |  | Completed |  | * RI - COMPL IN APT #210 DILLON BERRY UNIT 210 419-788-4213 | * MET WITH TODD/VILLAGE, TENANT NOT HOME. HALL LED LIGHT INSTALLED MOST FLOORS. THERMOSTAT NOT DONE, STATED LEAK IN CEILING WAS FROM A PIPE IN AN UPPER UNIT AND IT’S BEEN REPAIRED(?), CEILING TILES NOT DONE. GAVE TODD UNTIL END OF DAY TO PROVIDE PICTURE OF REPAIRS AND WILL WAIT UNTIL NEXT RAIN TO CLEAR LEAK VIOLATION. TCH * 8-9-21 CALLED DILLON - NO LM, TALKED TO FATHER CHRIS, TOLD HIM WHAT HAD BEEN PLANNED - WAITING FOR HEAVY RAIN WHICH HAPPENED AT 2:00 AM. WILL WAIT TO HEAR FROM DILLON. TCH * 8-10-21 UNABLE TO REACH DILLON (NO VM) TALKED WITH CHRIS (DAD) NO LEAK . COMPLAINT SATISFIED. TCH
21-62849 | CSD - Reinspection - Housing | 2021-10-07 | 2021-10-07 |  | Completed |  | * RI - APT #105 | * REPAIRS MADE - TENANT HAPPY. TCH
21-44403 | CSD - Reinspection - Housing | 2021-08-23 | 2021-10-15 | 2021-10-07 09:30 | Completed | NSD 09-Official Notice-1st Reinspection | * RI - CI - APT #105 + ENGINEER'S REPORT | * RI - NO ENGINEER'S REPORT, DOOR FRAME DAMAGED/CHISSELED TO MAKE DOOR SOME-WHAT FIT, FOUND EXISTING AND ONE ADDITIONAL BROKEN WASTE LINE IN NEED OF REPAIR. TALKED TO OSWALD - PF & TF + SEND FINAL N&O. THORIAN AGREED TO HANDLE FINAL RI DURING MY ABSENTS. TCH
21-54633 | CSD - No Show Inspection | 2021-10-15 | 2021-10-15 | 2021-11-01 09:00 | Completed | NSD 08 - Failure to Provide Access for Inspection | * SENDING FINAL N&O AFTER DISCUSSION WITH OSWALD. * THORIAN TO COVER RI, | 10-7-21 PER THORIAN - STATED HE WAS "NO SHOWED" WAS ABLE TO GET INTO BUILDIING BUT TENANT WASN'T HOME NOR DID MAINT SHOW UP. BILLING NS FEE. TCH TENANT - PATRICK BROWN FROM UNIT 105 563-320-4410. *10-15-21 CALLED TENANT FOR HIS WORK SCHEDULE SO THAT i CAN GET INTO UNIT. TCH * 10-21-21 WAS ABLE TO TALK WITH TENANT PATRICK BROWN WHO STATED HE WILL BE BACK AT THE APPARTMENT NOVEMBER 1ST. SENDING/EMAILING NO SHOW LETTER WITH 11-1-21 9:00 AM DATE, BILLING NS FEE. TCH
21-68742 | CSD - Rental Property Complaint Inspection | 2021-11-17 | 2021-11-17 |  | Completed |  | JENNA CRISTORFORO FROM APT 611 CALLED IN ABOUT NO HEAT ; ENTRY DOORS ARE SUPPOSED TO BE SECURE AND ARE NOT; ELEVATOR NOT WORKING AND NO PERMIT 319-217-2089 | * 11-17-21 MET WITH KYLE AND TALKED TO TENANT, HEAT IS WORKING. ALSO CHECKED ELEVATOR IS WORKING. TOLD TENANT THAT MAIN ENTRY DOORS ARE NOT REQUIRED TO LOCK. TWO FIRE EGRESS STAIRWELLS ARE CONFIRMED AND MARKED CORRECTLY. NO FURTHER ACTION REQUIRED. TCH
21-104315 | CSD - Debris Inspection | 2021-12-02 | 2021-12-02 |  | Completed |  | Trash from dumpster over filled and blowing all over other properties | Work dumpster is full but did not see anything falling out of it. This property currently has open permits for the work to be done. Nothing to enforce at this time. 12/2/21 stb
21-64101 | CSD - Reinspection - Housing | 2021-10-21 | 2021-12-09 | 2021-01-20 | Completed | NSD 15 - Notice to Vacate | * RI - COMPLAINT - APT #105 | * 11-1-21 @ 9:00 AM MET WITH TENANT PATRICK BROWN. PER BROWN, ONLY WORK DONE WAS SOME SANDING ON THE DOOR JAM. OWNER/MGR NO SHOWED OR RESPONDED. INFORMED TENANT OF PROCESS MOVING FORWARD AND WILL INCLUDE TENANT IN EMAILS MOVING FORWARD. * 12-9-21 TALKED WITH OSWALD, SENDING 30 DAY VACATE LETTER AFTER TALKING/COORDINATING WITH TENANTS TRAVELS. POSTING TAG LTR ON DOOR, COPY LETTER MAILED TO TENANT, MAILING LTR TO MGR & OWNER, EMAILING MGR & OWNER. BILLING RI FEE FOR TAGGING UNIT. TCH * 2-25-22 TALKED WITH TENANT AND OSWALD, GREED ON REMOVING TAG LTR WHICH ALLOWS TENANT TO STAY IN UNIT. TENANT WILL ADVISE ME IF PROBLEMS ARRISE. TCH
21-105267 | CSD - Rental Property Complaint Inspection | 2021-12-21 | 2021-12-21 |  | Completed |  | MICHAEL BREDEN FROM APT 603 HAS NOT HAD HEAT SINCE HE MOVED IN BACK IN SEPT. HE IS ON VA PROGRAM AND HIS LIASONS HAVE BEEN TRYING TO REACH LL ABOUT THIS BUT NOT GETTING ANY RESPONSE. HIS NUMBER IS 626-715-1429. HE GOES TO WORK AT 2 AND IS OFF ON FRIDAY | Attempted to contact multiple times, no contact. 12/21/21 TJT
21-107433 | CSD - Rental Property Complaint Inspection | 2021-12-21 | 2021-12-21 | 2021-12-27 10:00 | Completed |  | **Water coming through ceiling of grade level remodel NW corner. Wet in 405 as well. | Appears to be leak in shared wall between 505/unit to the south. That is traveling down and making its way through the ceiling of the suite being remodeled currently at thee NW corner of the building. Elevators were also down but have since been repaired. Sending notice 12/20/21 TJT Petersen plumbing was here for repairs sunday/monday. Confirmed with tenants, awaiting invoice from prop mgmt. 12/21/21 TJT
21-107611 | CSD - Rental Property Complaint Inspection | 2021-12-21 | 2021-12-21 |  | Completed |  | MALAYSIA CLAYTON FROM APT 615 CALLED IN 309-721-9562 ABOUT NOT HAVING HOT WATER FOR FOUR DAYS. SHE IS NOT GETTING RESPONSE FROM LL ABOUT THIS. ALSO FRONT DOOR SHE THOUGHT WAS SUPPOSED TO BE LOCKED BUT IS NOT SECURE -ISSUES WITH HOMELESS PEOPLE GETTING IN BUILDING | Resolved. Pertained to the issue that was causing the water leaking from 5th or 6th floor all the way to grade level. Petersen has been into make the repairs on Sun/Mon. Hot water issues have been resolved based off subsequent repairs. 12/21/21 TJT
21-48185 | ELECTRICAL PERMIT | 2021-08-05 | 2022-01-21 |  | Completed |  | REPLACE ILLEGAL WIRING, LIGHTING, AND DEVICES FOR CODE COMPLIANCE | DBL FEE - CAUGHT DOING WORK UNDER OTHER MISC PERMIT
22-3568 | METER INSPECTION | 2022-01-20 | 2022-01-21 |  | Completed |  | ATTENTION: The applicant shall provide proper access to all mechanical and electrical equipment. Access shall include a secure ladder or other approved means to access furnace or roof-top equipment.
22-3567 | METER INSPECTION | 2022-01-20 | 2022-01-21 |  | Completed |  | ATTENTION: The applicant shall provide proper access to all mechanical and electrical equipment. Access shall include a secure ladder or other approved means to access furnace or roof-top equipment.
22-5225 | Environmental Clean Up | 2022-01-31 | 2022-01-31 |  | Completed |  | *IMMEDIATE CLEANUP-DUE TO DEBRIS SPREADING* REMOVE AND PROPERLY DISPOSE OF ALL LITTER, GARBAGE, CARDBOARD, PLASTIC TOTES, FLOOR COVERINGS, BOX SPRINGS, MATTRESSES, GROCERY CARTS, AND ALL OTHER DEBRIS THE DUMPSTERS Cleaned up 10:30 1/31/22 KGE BM | IMMEDIATE CLEANUP PER RICH OSWALD 1/31/22 STB
22-4840 | ELECTRICAL PERMIT | 2022-01-27 | 2022-02-02 |  | Completed |  | ADD GFCI RECEPTACLES, SWITCHES, SMOKE AND CARBON MONOXIDE DETECTORS.
22-4844 | ELECTRICAL PERMIT | 2022-01-27 | 2022-02-02 |  | Completed |  | ADD GFCI RECEPTACLES, SWITCHES, SMOKE AND CARBON MONOXIDE DETECTORS.
22-7276 | Environmental Clean Up |  | 2022-02-11 |  | Completed |  | *24HR NOTICE 10:20AM* REMOVE AND PROPERLY DISPOSE OF ALL LITTER, GARBAGE, MATTRESSES, AND ALL OTHER DEBRIS ALONG THE ALLEY *PICKED UP 1025 2/11/22 NL CH Property manager was emailed 2/10/22 stb | PER RICH OSWALD - THERE WAS MATTRESSES ALONG THE ALLEY AND WANTED ME TO CHECK IT OUT 2/10/22 STB
22-9105 | CSD - Rental Property Complaint Inspection | 2022-02-25 | 2022-02-25 |  | Completed |  | MATTHEW DENGER FROM APT 511 CALLED IN STATING NO HEAT FOR MONTHS. 239-841-1069 | Called 3 times no response 2/25/22 TJT
22-4843 | ELECTRICAL PERMIT | 2022-01-27 | 2022-03-01 |  | Completed |  | ADD GFCI RECEPTACLES, SWITCHES, SMOKE AND CARBON MONOXIDE DETECTORS.
22-4841 | ELECTRICAL PERMIT | 2022-01-27 | 2022-03-01 |  | Completed |  | ADD GFCI RECEPTACLES, SWITCHES, SMOKE AND CARBON MONOXIDE DETECTORS.
22-19349 | CSD - Rental Property Complaint Inspection | 2022-04-08 | 2022-04-11 |  | Completed |  | * TENANT RYAN (563) 505-5393 CALLED AND STATED NO HOT WATER THROUGHOUT BUILDING. | * SENDING EMAIIL TO SARAH/VILLAGE PROPER MGMT, SARAH NELSON, ANDREW WOLD & RICH OSWALD - TCH @11:17 AM- TALKED WITH KYLE/ALLIANCE MAINT. - STATED HE'S WORKING WITH KEVIN/PETERSON PLMB (370-2624) WHO CONFIRMED THE RECIRCULATION PUMP BEARINGS ARE BEING INSTALLED AND PUMP WILL BE OPERATING BEFORE END OF DAY. CALLING TENANT TO PASS ON WHAT I KNOW. TCH * 4-11-22 TALKED WITH TENANT RYAN - HOT WATER RESTORED. CLEARING COMPLAINT. TCH
21-104791 | ELECTRICAL PERMIT | 2021-12-06 | 2022-04-20 |  | Completed |  | ADDING RECEPTACLES, SWITCHES, CO & SMOKE DETECTORS IN APARTMENT #406
22-29371 | CSD - Debris Inspection |  | 2022-05-16 |  | Canceled |  | Owner of the davenport causing EPA level carnage on downtown. There is another roll off dumpster also overflowing with trash and debris.
22-19821 | CSD - Rental Property Complaint Inspection | 2022-04-12 | 2022-05-16 | 2022-05-16 10:41 | Completed |  | ABIGAIL LANE FROM APT 305 CALLED IN LEFT MESSAGE ON A/M REGARDING NO HEAT - 563-650-9964 HER ORGINAL REQUEST SUBMISSION IS BELOW-SHE HAS NOT HAD HEAT SINCE END JANUARY My heat and air have not been working. I have emailed my landlord four times and gotten no response. I have called the office number and left a voicemail and still no response. I have texted and no response still. This has been going on since January 20th. It's been almost three months with no heat in the winter and no air. | * 4-12-22 CALLED ABIGALE/TENANT @ 8:56 AM - LM ON VM. CALLED KYLE/ALLIANCE - HE TOLD ME HE'LL CALL PETERSON PLMB FOR A SERVICE CALL ON WEDNESDAY. CALLED ABIGALE TO INFORM HER - LM ON VM. TCH * 4-12-22 RECVD CALL FROM ABIGALE AT 1:22 PM - WAS TOLD THAT SHE'D BEEN CALLING PETERSON PLMB TRYING TO GET ANSWERS BECAUSE VILLAGE STOPPED CALLING BACK WITH INFO OR ANSWERS TO HER PROBLEM. I CALLED STEVE/PETERSON PLMB WHO TOLD ME THAT 303 & 305 UNITS ARE GETTING NEW UNITS BUT THE UNITS ARE BEING HELD UP AT THE MEXICAN BOARDER AWAITING TRUCK SHIPMENT. CALLED ABIGALE BACK TO INFORM HER OF THE HOLD UP AND TOLD HER THE MINUTE THE UNITS MAKE THE DOCK THAT PETERSON WILL CALL ME AND I WILL CALL HER. COMPLAINT PUT ON HOLD. CALLED KYLE - WENT TO VM. TCH * 4-13-22 TALKED WITH TENANT ABBY - PETERSEN PLMB DIDN'T SHOW AND THAT SHE'S REFUSING SPACE HEATERS. REPEATED WHAT I KNOW ABOUT REPLACEMENT IS BEING HELD UP AT MEXICAN BOARDER. TCH * 5-16-22 at 10:10 am - CALLED ABIGAIL IN REFERENCE TO THE REPLACEMENT OF THE HEATING ELEMENT IN HER APARTMENT. LM ON VM. ABBY CALLED BACK STATING NO REPLACEMENT YET. ADVISED HER HEAT IS NOT REQUIRED AT THIS TIME AND TO CALL BACK IN OCTOBER IF HEAT IS NOT FIXED. TCH
22-28314 | CSD - Debris Inspection | 2022-05-11 | 2022-05-17 | 2022-05-23 11:41 | Completed |  | REMOVE AND PROPERLY DISPOSE OF ALL GARBAGE, LITTER, PLASTIC BAGS, CARDBOARD, SCRAP WOOD, MATTRESSES AND ALL OTHER DEBRIS ON THE ENTIRE PROPERTY AND ALL DEBRIS ON PARCELS: L0007-25A, L0007-25, L0007-26 AND L0007-28. | Complaint:Two overflowing dumpsters Latest offense of multiple Contributing to litter blowing everywhere downtown Complaint came in for 325 Harrison st but I believe the debris they are referring to is the dumpsters at 324 Main. Will change asset and send debris letter. BMA 5/11/22, 11:42 AM Per Rich - Turning in for an immediate clean up since more debris has accumulated. Closing task. BMA 5/17/22, 9:19 AM
22-29932 | Environmental Clean Up | 2022-05-17 | 2022-05-17 |  | Completed |  | REMOVE AND PROPERLY DISPOSE OF ALL GARBAGE, LITTER, PLASTIC BAGS, CARDBOARD, SCRAP WOOD, MATTRESSES AND ALL OTHER DEBRIS ON THE ENTIRE PROPERTY AND ALL DEBRIS ON PARCELS: L0007-25A, L0007-25, L0007-26 AND L0007-28. cu 5/17/22 13:21 jd/rb
22-40255 | PLUMBING PERMIT | 2022-06-09 | 2022-06-10 |  | Completed |  | REPLACE PLUMBING FIXTURES
22-40778 | CSD - Administrative | 2022-06-11 | 2022-06-11 |  | Completed |  | DEEMED NUISANCE PROEPRTY
21-104790 | ELECTRICAL PERMIT | 2021-12-06 | 2022-06-24 |  | Completed |  | ADD RECEPTACLES, SWITCHES, CO & SMOKE DETECTORS IN APARTMENT #306
22-36403 | CSD - Graffiti Abatement | 2022-05-23 | 2022-06-27 |  | Completed |  | * south side of building. | * HANDLED BY DDP POWER WASHER. TCH
21-106819 | ELECTRICAL PERMIT | 2021-12-16 | 2022-07-01 |  | Completed |  | RECEPTACLES, SWITCHES, SMOKE/CO DETECTORS
22-44066 | Environmental Clean Up | 2022-06-30 | 2022-07-01 |  | Completed |  | * NUISANCE ABATE - OVERFLOWING DUMPSTER - PLEASE PICK UP ALLL LOOSE TRASH IN THE PARKING LOT AND LEVEL DUMPSTER. complete “ dumpster lids were locked, and unable too level lid 7/1/22 TH SE 09:20
22-45478 | PLUMBING PERMIT | 2022-07-07 | 2022-07-08 |  | Completed |  | REMODEL, REPLACE WATER CLOSET AND KITCHEN FIXTURES.
22-45383 | PLUMBING PERMIT | 2022-07-07 | 2022-07-08 |  | Completed |  | Unit #202 caulk around the water closet base and the lavatory, install a trap for the lavatory, install the drain for the kitchen sink, and test the fixtures for leaks. Unit #211 install a water closet with seat, caulk around the water closet base and the lavatory, modify the drain, trap arm, and install a trap for the lavatory, modify the drain, trap arm, and install a trap for the kitchen sink, install the dishwasher, and test the fixtures for leaks. Unit #215 caulk around the water closet base and the lavatory, modify the drain, trap arm, install a trap and 2-water supply connectors for the lavatory, modify the drain, trap arm, and install a trap for the kitchen sink, and test the fixtures for leaks.
21-54592 | PLUMBING PERMIT | 2021-09-03 | 2022-07-20 |  | Completed |  | REPLACE STOPS IN KITCHEN, LAV, AND WATER CLOSET IN 20 UNITS
22-48870 | CSD - Weed Abatement | 2022-07-21 | 2022-07-26 |  | Completed |  | * CUT AND TRIM ALL TALL GRASS, WEEDS AND SCRUB VEGETATION FROM THE ENTIRE PARCEL | grass and weeds over 12" cut 7-26 - jr
22-48735 | CSD - Nuisance Abate/Inspect | 2022-07-26 | 2022-07-26 |  | Completed |  | Debris in parking lot, and around dumpster area. Property also has overgrown weeds. | * working with Kyle and Sarah. RI found property cut and somewhat cleaned up.
22-50405 | Environmental Clean Up | 2022-07-28 | 2022-07-28 |  | Completed |  | * NUISANCE PROPERTY - EMERGENCY CLEAN UP AT OVERFLOWING DUMPSTER AND ON GROUND AROUND DUMPSTER - GARBAGE GAGES, CARPETING, CARDBOARD BOXES PLASTIC CONTAINERS, LOOSE TRASH AND DEBRIS cu 7/28/22 12:02 jd | * CALLED JEFF GOOD WITH HEADS UP. TCH
22-42130 | MECHANICAL PERMIT | 2022-06-17 | 2022-08-02 |  | Completed |  | 12,000 BTU HEAT PUMP
22-42136 | MECHANICAL PERMIT | 2022-06-17 | 2022-08-02 |  | Completed |  | 24,000 BTU
22-51633 | Environmental Clean Up | 2022-08-03 | 2022-08-03 |  | Completed |  | *NUISANCE PROPERTY* REMOVE AND PROPERLY DISPOSE OF ALL LITTER, GARBAGE, CARDBOARD, PLASTIC BAGS, FLOOR COVERINGS, AND ALL OTHER DEBRIS AT THE COLLECTION POINT AND PARKING LOT complete 8/3/22 14:08 LL CJ
22-53816 | Environmental Clean Up |  | 2022-08-15 |  | Completed |  | * NUISANCE CLEAN UP - LOOSE TRASH AND DEBRIS ON GROUND AT DUMPSTER AND THROUGHOUT THE SOUTH SIDE OF THE PARK LOT complete 8/15/22 08:18 LL SE | * INFORMED JEFF GOOD VIA PHONE CALL. TCH
22-53166 | CSD - Exterior Property Maintenance | 2022-08-10 | 2022-08-15 | 2022-09-15 | Completed | NSD 04 - Complaint Notice and Order | broken window. could be dangerous to public. | * APPEARS TO BE A ROCK OR BULLET HOLE IN THE EAST 1ST FLOOR STREET SIDE WINDOW, THIRD FROM ALLEY. . CALLED KYLE TO GIVE DIRECTIONS TO THE BROKEN. DOESN’T APPEAR TO BE DANGEROUS AT THE TIME BEING. TCH * 8-15--22 COMPLAINT LTR SENT REG MAIL + EMAILED TO SARAH. KYLE AND ANDREW. TCH
22-54810 | CSD - Rental Property Complaint Inspection | 2022-08-17 | 2022-08-18 | 2022-09-01 08:00 | Completed | NSD 04 - Complaint Notice and Order | Elizabeth Turner from #302 (563-514-8517) came in and spoke with Denise -upstairs apt leaking into her bathroom; mold has doubled, she was told it was fixed. She has pics and videos of issue | * MAILED & EMAILED WOLD, VILLAGE & ALLIANCE. TCH * 9-1-22 TALKED TO TENANT - SHE MOVED OUT AND KYLE/VILLAGE ADMITTED WORK WAS NOT DONE IN APARTMENT. KYLE WANTED TO MOVE RI TO FRIDAY. TCH
21-55724 | PLUMBING PERMIT | 2021-09-10 | 2022-09-12 |  | Completed |  | REPLACE WATER STOPS FOR THE KITCHEN, LAVATORY, AND WATER CLOSET IN 40 UNITS
22-60467 | Environmental Clean Up | 2022-09-16 | 2022-09-16 |  | Completed |  | * NUISANCE PROPERTY - OVERFLOWING DUMPSTER, LOOSE TRASH AND DEBRIS AROUND DUMPSTERS AND THROUGHOUT PARKING LOT AND ALLEYWAY complete/ picked all bulky and 90% loose garbage wasp everywhere 9/16/22 14:00 LL SE | * COMPLAINT: Dumpster Overflowing for over a week.
22-60894 | PLUMBING PERMIT | 2022-09-19 | 2022-09-22 |  | Completed |  | ADD LAVATORY IN #605
22-54179 | CSD - Reinspection - Housing | 2022-08-15 | 2022-09-26 | 2022-09-26 08:35 | Completed |  | * RI - CI INSPECTION ON BROKEN WINDOW. | * WINDOW REPAIRED WITH VISUAL CHECK BY ME. TCH
22-55067 | CSD - Reinspection - Housing | 2022-09-28 | 2022-09-28 | 2022-09-28 09:02 | Completed | NSD 17 - Vacant Re-Occupy | * RI (CI) APT #302 | * APT # 302 IS VACANT - CEILING LEAK/BATH + PLASTER REPAIR. SENDING INSPECT B4 RE-OCCUPING. LTR SENT REG/CERT MAIL + EMAILED. RI FEE & PF X 2 BILLED. TCH 10/24/22 CERT MAIL RETURNED FROM PO BOX 611-HB
21-66754 | PLUMBING PERMIT | 2022-05-26 | 2022-09-29 |  | Completed |  | FIXTURES OF 35 UNITS AND 2 COMMERCIAL SPACES. 113 FIXTURES 104, 201, 203, 204, 207, 302, 303, 304, 308, 311, 312, 316, 317, 409, 411, 413, 416
22-61711 | PLUMBING PERMIT | 2022-09-23 | 2022-09-29 |  | Completed |  | INSTALL PLUMBING FIXTURES.
22-62560 | PLUMBING PERMIT | 2022-09-27 | 2022-09-29 |  | Completed |  | INSTALL FIXTURES
22-62753 | PLUMBING PERMIT | 2022-09-28 | 2022-09-29 |  | Completed |  | Install a lavatory, water closet, trim bathtub faucet, and install the kitchen sink.
22-62751 | PLUMBING PERMIT | 2022-09-28 | 2022-09-29 |  | Completed |  | INSTALL FIXTURES AND TRIM OUT
21-33468 | CSD - Reinspection - Housing | 2021-06-28 | 2022-10-10 |  | Completed |  | * FINAL RI | * 6-25-21 EMAIL RECIEVED : Tony, We will be starting the work at the 324 Main building the first week of July weather permitting. Thanks, Chris (Belser - Bi-State Masonry). TCH * 8-2-21 RI ON EXISTING VIOLS ON HOLD PER RICH OSWALD. TCH * 10-10-22 EXTERIOR BRICK REPAIR COMPLETED AND SIIGNED OFF BY TRISHNA. TCH
22-66801 | Environmental Clean Up | 2022-10-18 | 2022-10-18 |  | Completed |  | IMMEDIATE CLEAN UP 10/18/22 12:00PM ATA REMOVE AND PROPERLY DISPOSE OF ALL TRASH, CARBOARD, PLASTIC BAGS, MATTRESSES, CANS, AND ALL OTHER DEBRIS FOUND ON THE ENTIRE PROPERTY. 10/18/22 emailed mgmt-hb cu, the rug is underneath the dumpster. 10/18/22 14:30 jd
22-67867 | Environmental Clean Up | 2022-10-24 | 2022-10-24 |  | Completed |  | * NUISANCE PROPERTY - LOOSE TRASH BAGS, CARDBOARD BOXES, RAW GARBAGE AND DEBRIS ON GROUND AT DUMPSTER. cu 10/24/22 13:36 jd
22-68530 | CSD - Reinspection - Housing | 2022-10-28 | 2022-10-28 |  | Completed |  | * RE-INSPECTION OF APT #302 | * VIOL SATISFIED. TCH
22-71507 | Environmental Clean Up | 2022-11-14 | 2022-11-15 |  | Completed |  | IMMEDIATE CLEAN UP 11/14/22 11:00AM ATA REMOVE AND PROPERLY DISPOSE OF ALL TRASH, CARDBOARD, PLASTIC BAGS, BOTTLES, CANS, AND ALL OTHER DEBRIS FOUND ON THE ENTIRE PROPERTY. cu 11/15/22 11:04 jd
22-75325 | Environmental Clean Up | 2022-12-06 | 2022-12-06 |  | Completed |  | *NUISANCE PROPERTY* PLEASE REMOVE ALL TRASH, LITTER, CARDBOARD, CANS, BOTTLES, CLOTHING, STYROFOAM, BAGS, AND ALL OTHER DEBRIS AROUND DUMPSTER cu 12/6/22 13:29 jd/eb
22-76324 | Environmental Clean Up | 2022-12-13 | 2022-12-14 |  | Completed |  | ***24 HOUR NOTICE 12-13-22 AT 3:00 PM*** PLEASE REMOVE AND PROPERLYDISPOSE OF ALL TRASH, GARBAGE, GARBAGE BAGS, CARDBOARD BOXES, PLASTIC, FOOD WRAPPERS, PAPER, AND ALL LOOSE DEBRIS SURROUNDING THE DUMPSTER AND ON THE ENTIRE PROPERTY. cu 12/14/22 07:48 jd | Complaint: Dumpster is overflowing and has trash surrounding it. Debris complaint turned in to a 24 hour notice. 12-13-22 RJM
22-72409 | CSD - Rental Property Complaint Inspection | 2022-11-17 | 2022-12-19 |  | Completed |  | * COMPLAINT OF WATER RUNNING FROM ROOF AND POOLING AT ALLEY. | * TALKED WITH KEVIN/PERTERSON - LARGE HOLE ON HEAT EXCHANGER ON COOLING TOWER. ASSISTED KEVIN WITH PROCEDURE OF VALVES TO BYPASS AND SHUT WATER OFF GOING TO TOWER. PER KEVIN, ROOF TOP TOWER LINES OCCLUDED AND COMPLETE UNIT NEEDS REPLACED. WILL CONTINT MESSAGE TO KEVIN WITH PETERSON PLUMBING CONCERNING WATER DRAINING FROM COOLING TOWER ON ROOF. TOLD KYLE TO ADDRESS WATER DRAINING ACROSS THE MAIN ST DRIVEWAY AND SIDEWALKS AT THIS POINT. TCH NUE TO HAVE HEATING PROBLEMS UNTIL A SECONDARY WATER SCRUBBER SYSTEM IS INSTALLED. TCH * 12-19-22 WATER LEAK HAS BEEN CONTROLED. TCH
22-76985 | CSD - Rental Property Complaint Inspection | 2022-12-28 | 2022-12-28 |  | Completed |  | TODD WILSON FROM #209 CALLED IN STATING HIS HEAT DOES NOT STAY ON -WAS DOWN TO 48 DEGREES YESTERDAY. NO HOT WATER IN BATHROOM TUB 571-842-3838 | * 12-15 THRU 16-22 OFF ON MEDICAL LEAVE. TCH * 12-19-22 AT 9:12 AM - CALLED TENANT - UNABLE TO LEAVE MESSAGE OR PHONE NUMBER. TCH * 12-20-22 EMAIL FROM MGR: Tony unit 209 has hot water and it’s 68 degrees in his apartment right now. I need to put a new tub spout on so his shower works. TCH * 12-28-22 NO CONTACT WITH COMPLAINANT - CLOSING TASK. TCH
23-110 | Environmental Clean Up | 2023-01-04 | 2023-01-04 |  | Completed |  | ***NUISANCE DUMPSTER IMMEDIATE CLEAN UP*** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, BOTTLES, CANS, CLOTHING, WOOD PIECES, AND ALL OTHER DEBRIS AROUND THE DUMSPTER SITE 1/4/23 ATA Complete 1/4/23 12:00 LL EB
23-2176 | Environmental Clean Up | 2023-01-12 | 2023-01-12 |  | Completed |  | *immediate clean up* trash and debris around dumpster and dog waste on sidewalks and in the alley around the building normally we do not address dog waste but since this is on the ROW needs removed. GL cu, the remaining debris is under the dumpster. 1/12/23 10:34 jd
23-3046 | Environmental Clean Up | 2023-01-18 | 2023-01-18 |  | Completed |  | ***NUISANCE DUMPSTER*** 24 HOUR NOTICE POSTED 1/18/23 8:00AM PLEASE REMOVE AND PROPERLY DISPOSE OF ALLT RASH, LITTER, PLASTIC BAGS, PAPER, CARDBOARD, AND ALL OTHER DEBRIS SURROUNDING DUMPSTER 1/18/23 EMAILED MGMT -HB 1/18/23 1:00 TH NL Complete
23-3812 | CSD - Rental Property Complaint Inspection | 2023-01-23 | 2023-01-25 | 2023-01-27 10:00 | Completed | NSD 04 - Complaint Notice and Order | JOSEPH WATSON FROM APT 203 CALLED IN STATING NO HEAT FOR LAST TWO WEEKS 563-570-8151 | 1/23/23 - Beth asked if I could do this task as Tony is sick today. I tried calling tenant but it went to voicemail. I left a message for him to return my call- Tpv 1/23/23 - Spoke to tenant Joe and have scheduled CI for 1:00pm tomorrow afternoon - Tpv 1/23/23 - Spoke to assistant manager Libby on the phone and told her I was meeting with tenant Joe tomorrow at 1:00pm. She said she was not sure if she or maintenance was available to meet - Tpv 1/24/23 - When I pulled up to the building, Libby and manager Sara Tyler was walking up. I assumed it was to go with me to Joe’s unit # 203 but they said they were there for something else and chose not to join me. The let me in the building to do the complaint inspection on my own. Sara did tell me that Peterson heating was in #203 a week and a half ago and a part is on order for the heating unit in Joe's apartment. She stated they are at “the mercy” of Peterson and have no idea when the part will be in for repair. I asked if they could offer Joe a different unit to move into in the meantime and they said they would have to ask the owner. I also relayed to Sara & Libby that the tenant Joe is concerned about the extra utility expense of running the space heater as he is on a very fixed budget. Again they said they would have to check with the owner. I then went up and met with Joe in unit 203. Temperature in his unit is sitting at 62 degrees with his space heater running. He said the heat went out on Jan 6th and the maintenance or Peterson arrived on Jan 13th. While there, they told Joe that “a whole new heating unit is needed”, and then left and did not put the ceiling tiles back in place. Joe said his patience is running thin as he’s been without heat for so long and he does not hear anything from management besides a couple of e-mails that don’t give him any answers. I will check with Tony when he returns tomorrow to see how he wants to handle this and go from there - Tpv 1/25/23 - Spoke to Kevin from Peterson heating (563-370-2624) and he said it has been at least a month and a half since any technician has been to this property due to credit holds for lack of payment from owner/management. Tony is back today and said he will take over as he is more familiar with management situation. Charging CI penalty fee - Tpv * 1-25-23 CALLED TENANT - LET HIM KNOW I AM SENDING OUT 48 HR NOTICE TO RESTORE HEAT. LTR SENT EMAIL & REG MAIL. TCH
23-4184 | CSD - Rental Property Complaint Inspection | 2023-01-24 | 2023-01-25 | 2023-01-27 10:00 | Completed | NSD 04 - Complaint Notice and Order | COURTNEY FRITZ FROM #303 CALLED IN NO HEAT SINCE DECEMBER AND NO ANSWER FROM THE MGMT 309-251-7469 - ASSIGNED TO BOTH TOM AND TONY AS TONY OUT ILL AND TOM SCHEDULED INSP FOR ANOTHER TENANT FOR TOMROW | 1/24/23 @ 8:15am - Left a message for tenant to return my call - Tpv 1/24/23 @ 1:30pm - While I was at another complaint inspection in the same building, I knocked on unit #303 to see if Courtney was home but there was no answer - Tpv * 1-25-23 talked to the tenant to explain that I am working on returning the heat. 48 hr notice emailed and mailed. TCH
23-4950 | Environmental Clean Up | 2023-01-26 | 2023-01-27 |  | Completed |  | ***NUISANCE DUMPSTER IMMEDIATE CLEAN UP*** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, BOTTLES, CANS, AND ALL OTHER DEBRIS AROUND THE DUMSPTER SITE 1/26/23 ATA Cleaned up 1/27/23 10:40am CJ MP
23-4580 | CSD - Reinspection - Housing | 2023-01-25 | 2023-01-30 | 2023-02-09 | Completed | NSD 15 - Notice to Vacate | * RI - CI OF NO HEAT IN APT #203 | * 1-27-23 Re-inspection found temp in living room with space heater showed 66 deg, bedroom showed 59 degrees. Was told by Jessie/maint. that heating unit no longer repairable and needs to be replaced. tch * 1-30-23 talked with tenant - he is living at motel. Told him that I am tagging unit for a ten day vacate . I called Amy Pake - Humility Housing and made her aware that I was tagging unit and that she will need to find Joe someplace to live. TCH
23-5467 | CSD - Rental Property Complaint Inspection | 2023-01-30 | 2023-01-30 | 2023-02-09 11:00 | Completed | NSD 04 - Complaint Notice and Order | * JASMIN DELGADO (3314229123) JASMINDELGADO11@GMAIL.COM ALFREDO ALVAREZ (6309457155) ALVAREZ15ALFREDO@GMAIL.COM * APT # 604 - HEAT COMPLAINT - NO HEAT FOR SINCE OCTOBER 2022. | * SPACE HEATER BEING USED SINCE MOVING IN. TEMP SHOWN WAS 1ST FLOOR WITH SPACE HEATER ON. PER JESSIE, COMPRESSER/HEATING UNIT INOPERABLE. MAILED AND EMAILED DH & MGR TCH
23-4576 | CSD - Reinspection - Housing | 2023-01-25 | 2023-01-31 | 2023-02-01 15:57 | Completed |  | * RI OF CI - APT #303 FOR NO HEAT. | * TAGGED PROPERTY FOR 10 DAY VACATE , EMAILED AND MAILED VACATE LETTER TO VILLAGE & OWNWER. TENANT LIVING IN MOTEL AND NOT IN APT. HUMILITY HOMES NOTIFIED. TCH * 2-1-23 call from tenant - heat is back on. TCH
23-6319 | Environmental Clean Up | 2023-02-02 | 2023-02-02 |  | Completed |  | ***NUISANCE DUMPSTER IMMEDIATE CLEAN UP*** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, BOTTLES, CANS, METAL, STYROFOAM, AND ALL OTHER DEBRIS AROUND THE DUMSPTER SITE Cleaned up 2/2/23 11:25am CJ MP
23-6691 | CSD - Debris Inspection | 2023-02-02 | 2023-02-02 | 2023-04-17 10:30 | In Progress | NSD 05 - Debris Letter | * BASEMENT LEVEL; REMOVE AND PROPERLY STORE ALL SAVED BUILDING MATERIAL ITEMS OUTSIDE A 50' RADIUS OF ALL MECHANICAL & ELECTRICAL DEVICES AND FROM WALKWAYS AND DOORWAYS . REMOVE AND PROPERLY DISPOSE OF ALL LOOSE AND DAMAGED CONSTRUCTION MATERIALS, PLASTIC PAILS, SCRAP METALS, INSULATION, CARDBOARD AND CARDBOARD BOXES, LOOSE/EMPTY METAL FREON TANKS, FULL GARBAGE CONTAINERS, AND LOOSE TRASH. | * PER OSWALD, SENDING A DEBRIS LETTER IN THE BASEMENT PAYING CLOSE ATTENTION TO THE AREA AROUND THE BOILER. INFORMED SARAH/VILLAGE OF THE LETTER, SENT REGULAR AND EMAIL. TCH * 3-10-23 SENDING A 2ND LTR - FINAL DEBRIS LTR PER OSWALD. TCH
21-68030 | MECHANICAL PERMIT | 2021-11-10 | 2023-02-03 |  | Completed |  | BOILER REPLACEMENT
21-106809 | ELECTRICAL PERMIT | 2021-12-15 | 2023-02-03 |  | Canceled |  | DISCONNECT AND RECONNECT BOILER
23-6517 | Environmental Clean Up | 2023-02-03 | 2023-02-03 |  | Completed |  | ***NUISANCE DUMPSTER*** IMMEDIATE CLEAN UP PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, REFRIGERATORS, METAL PIECES, AND ALL OTHER DEBRIS SURROUNDING THE DUMPSTER AND LOT TO THE LEFT Debris and plastic bags frozen to ground. could not get some of it. 2/3/23 12:08 MA ABE | COMPLAINT: dumpster at Davenport Hotel (324 Main Street) has a refrigerator with its doors attached sitting outside the dumpster. Please issue an emergency cleanup
23-4740 | CSD - Rental Property Complaint Inspection | 2023-01-26 | 2023-02-07 |  | Completed |  | LEIASHA ALGER FROM APT 306 STATES HER POWER HAS BEEN TURNED OFF FOR 24 HOURS AND SHE IS NOT ABLE TO REACH THE LANDLORD. SHE SD THAT POWER IS IN OWNERS NAME HER NUMBER 309-292-4467 | * 1-26-23 at 7:42 am - attempted call to tenant. No answer, no voicemail set up. Sent email copy of complaint to Village Properties, Wold, Oswald and Bringolf. TCH * 1-26-23 at 8:28 am - attempted call to tenant. No answer, No voicemail. tch * 1-26-23 email from Sarah: Utilities are her responsibility, so I will not be placing them into my name. She also hasn’t paid rent since October. So, I was serving her and eviction this week also. When I get to the office I will scan her lease to you! * 1-27-23 at 8:30 am - tried calling tenant - no answer but she called back at 9:00 am - tenant stated her case worker from Family Resources who is to be paying her rent and electricity. Told her she needs to contact Supervisor asap because there was a 3 day Quit served. Offered to talk to FR if they call me. tch * 1-30-23 called tenant - she stated she is working with Family Resources. TCH * 2-7-23 Per tenant - no longer living at property . Has eviction court today. TCH
23-6543 | CSD - Rental Property Complaint Inspection | 2023-02-07 | 2023-02-07 |  | Completed |  | MICHELLE VIVIAN FROM UNIT 606 (773-454-0338). NO HEAT SINCE SHE HAS LIVED THERE; UNDER KITCHEN SINK CABINET DOORS CAN BE PULLED OFF | * 2-3-23 sent complaint to Sarah who stated heat is working but tenant wants it hot in her apt. Video sent by maint. man Justin. TCH * 2-7-23 talked to tenant Michelle, heat problem was fixed. TCH
23-5411 | CSD - Reinspection - Housing | 2023-01-30 | 2023-02-09 |  | Completed | NSD 17 - Vacant Re-Occupy | * VI - APT #203 VACATE EXPIRATION. | * NO CORRECTIONS MADE PER JESSIE/MAINT. - APT COMPRESSOR INOPERABE. TENANT LIVING IN MOTEL. TCH * 2-9-23 @ 11:00 AM - TENANT HAS MOVED OUT, APT VACATED. SENDING "INSPECT B4 REOCC" LTR - SENT EMAIL, REG/CERT MAIL + POST ON APT DOOR. TCH
23-6918 | CSD - Rental Property Complaint Inspection | 2023-02-06 | 2023-02-09 | 2023-02-28 10:30 | Completed | NSD 04 - Complaint Notice and Order | * FIRE VIOLATIONS NOTED DURING WALK-THROUGH. | * SENDING COMPLAINT VIOL NOTICE AFTER COMPLANT WALK THROUGH.
23-5578 | CSD - Reinspection - Housing | 2023-01-30 | 2023-02-10 | 2023-02-27 | Completed | NSD 15 - Notice to Vacate | * RI - COMPLAINT OF NO HEAT IN APT #604 | * 2-9-23 @ 1:08 PM - RECVD TEXT FROM MAINT STATING HEAT WAS RESTORED. CALLED TENANT JASMMIN WHO STATED HEAT COMING FROM A FEW REGISTERS BUT NOT ALL. CALLED JUSTING - LM ON VM TO MEET ME AT 604 AT 2:30 PM. TCH
23-5613 | CSD - Reinspection - Housing | 2023-01-31 | 2023-02-10 |  | Completed |  | * RI - CI APT #604 - HEAT COMPLAINT. | 2-9-23 HEAT RETURNED TO UNIT THRU MIDWEST MECHANICAL. TOOK TEMP READINGS ON LOWER AND UPPER SECTIONS OF APT. TCH
23-8238 | CSD - Rental Property Complaint Inspection | 2023-02-13 | 2023-02-14 | 2023-03-14 10:00 | Completed | NSD 01 - Notice and Order | * CI - APT #606 MICHELLE/TENANT COMPLAINT OF NO HEAT . | 2.13.2023 went with Tony for heat / apartment inspection. jab * 2-13-23 VISITED APARTMENT TO FIND HEAT WAS SUFFICIENT/COMPLIANT (SEE PICS) BUT DID NOTESMOKE DETECTORS WHERE BATTERIES HAVE BEEN TAKEN OUT AND INOPERABLE. WILL SITE APARTMENT FOR VIOLS WITNESSED. NOT BILLING PF DUE TO ORIGINAL COMPLAINT WAS UNFOUNDED. TCH
23-10469 | Environmental Clean Up | 2023-02-24 | 2023-02-27 |  | Completed |  | * NUISANCE ABATEMENT - ORDERED FULL DUMPSTER AND GROUND AROUND DUMPSTER CLANED UP - REMOVE CLOTHING, TRASH BAGS, CARDBOARD, LOOSE TRASH, BAG OF TRASH, LOOSE DEBRIS. Cleaned up 2/27/23 8:43am CJ MP | * CALLED JEFF GOOD AT 2:56 PM - NO TRUCK AVAILABLE TO ABATE. TCH
23-11676 | CSD - Late Cancellation | 2023-02-28 | 2023-02-28 | 2023-04-17 10:00 | Completed | NSD 08 - Failure to Provide Access for Inspection | * RI - COMMON AREA FIRE VIOLATIONS. | * 2-28-23 AT 10:30 AM - I as at the property today for a re-inspection of complaint notice from February 6th, 2023 task # 23-6918 for 7 fire violations throughout the building. Met with maintenance, Kyle and Jessie, as they were driving by who stated that none of the work was completed. Kyle requested a late cancellation. Sending same day cancellation, bill fee and sending ltr reg mail & email. TCH
23-11630 | CSD - Reinspection - Other | 2023-02-28 | 2023-02-28 |  | Completed |  | * RI FOR DEBRIS IN BASEMENT | * 2-27-23 AT 3:19 PM - RECIEVED A CALL FROM SARAH TYLER/VILLAGE MGMT - TOLD ME OWNER/ANDREW WOLD REFUSES TO CLEAN UP DEBRIS IN BASEMENT AND THE "DEBRIS IS NOT A CODE VIOLATION BECAUSE TENANTS ARE NOT ALLOWED IN BASEMENT". I ADVISED HER OTHERWISE AND INFORMED DIRECTOR OSWALD. TCH * 2-28-23 AT 10:49 AM - RECIEVED EMAIL FROM SARAH; Tony and Rich, I spoke with Tony yesterday regarding cleaning the debris out of the basement at 324 Main Street. I told him that Andrew has advised that we will not be cleaning it out as that is where he is storing things during construction. None of our tenants have access to the basement, therefore Andrew did not deem it necessary to complete this task, and will not be performing a clean up of the basement. I told Tony this would not be done, and spoke with him on 2/27 to advise him of such. An inspection was missed today pertaining to this even though I told Tony we didn't have it complete, and would not be present for the inspection as the owner has not cleaned the area up of the storage material. I just wanted everyone to be aware and on the same page on this particular task/ item. If there are future issues to discuss regarding the basement, Rich- Please contact Andrew or email this thread back to the team. I appreciate your understanding in this matter as we work to complete the necessary tasks asked of us by the city at 324 Main Street. Thank you,Sarah Tyler, * 3-1-23 AT 11:21AM RICH OSWALD EMAIL RESPONSE TO SARAH; Refusal to clean the basement area is not acceptable or an option to discontinue enforcement of a Notice and Order. The debris that is referred to is not construction-type material. It can be combustible and poses a substantial risk to any emergency crews that could respond. It can also become an area for insects or rodents to nest. I am requesting a time to meet with you and Andrew at the property. I will ask the Fire Marshal to attend this meeting. Failure to comply with any notice and order can ultimately result in the revocation of the building rental license. I have attached a few pictures taken at the inspection. * 3-1-23 AT 2:40 PM SARAH'S EMAIL; Rich and Tony, I have spoken with Andrew and he has agreed to clean out the area. However, this will involve several trades to break down and remove some of the waste that has been sitting there for years. This debris is not from us, and this will be a costly, timely job. This debris is from up to if not more than two owners ago. They have always used this area for storage as this is a completely unoccupied area of the property. We will need the time to budget and line up crews to complete this task. With that being said, can we please get 60-90 days to have this completed and inspected? Again, we will need to plan and budget accordingly for this and we want to make sure its completed properly. Thank you for your consideration in this matter, Sarah Tyler * 3-2-23 AT 1:35 AM - RICH RESPONDED ON EMAIL; Sarah, Before any extension I would still like to have a meeting. TCH * 3-10-23 TALKED WITH RICH ABOUT FURTHER ACTION, PER RICH i WAS TO SEND ANOTHER LETTER WITH AN APRIL 17TH RE-INSPECTION FOR THE TRASH IN THE BASEMENT. TCH * 4-17-23 PER JIM MORRIS ALL DEBRIS REMOVED.- CLEARING VIIOLATIONS. TCH.
23-10951 | Environmental Clean Up | 2023-02-28 | 2023-02-28 |  | Completed |  | * NUISANCE CLEAN UP - LOOSE TRASH BAGS, LOOSE DEBRIS, OVERFLOWING DUMPSTER AT THE REAR OF THE PROPERTY. picked up 2/28/23 1:32 MP/TH | * CALLING SOLID WASTE (JEFF GOOD) TO INFORM THEM OF THE NUISANCE CLEAN UP. TCH
23-11748 | Environmental Clean Up | 2023-03-03 | 2023-03-03 |  | Completed |  | *IMMEDIATE CLEAN UP* PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH AROUND DUMPSTER COMPLETED 3/3/23 1:06 KA KG
23-12047 | Environmental Clean Up | 2023-03-06 | 2023-03-06 |  | Completed |  | *IMMEDIATE CLEAN UP* PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH AND DEBRIS AROUND DUMPSTER oc 3/6/23 12:58 jd/ch
23-12021 | CSD - Debris Inspection | 2023-03-06 | 2023-03-06 |  | Completed |  | DUMPSTER OVERFLOWING -THIS IS NUISANCE PROPERTY | *3-6-23 TURNED INTO IMMEDIATE ECU #23-12047, CALLED SW. GL
23-12859 | Environmental Clean Up | 2023-03-09 | 2023-03-09 |  | Completed |  | * NUISANCE CLEAN UP - LOOSE TRASH AND DEBRIS THROUGH OUT THE PARKING LOT WEST OF THE BUILDING. cu 3/9/23 13:25 jd | * @11:25 AM - CALLED JEFF GOOD TO NOTIFY OF CLEAN UP.
23-13477 | CSD - Rental Property Complaint Inspection | 2023-03-13 | 2023-03-14 |  | Completed |  | * COMPLAINT: On Sunday morning we were dispatched to a fire alarm at the Landmark Apartments on Main St. While investigating, we encountered the back stairway to the basement completely obstructed with garbage cans, and trash thrown down the stairs. The exits were completely obstructed as well as the landing of the back stairway, leading outside from the fire exit. I would recommend having the health department get involved with the open bags of trash both in the first floor, and all over the basement floors. The boiler was making some loud noises that did not seem to be normal, and the alarms were sounding on the boiler panel. Ceiling tiles were laying on the first floor hall way off of the 4th st. entrance between envied clothing and 4th st nutrition. In my opinion there are several health and safety violations that put the residents in harms way. Captain Terrell | * TALKED WITH MORRIS AND WILL MEET WITH HIM AT 324 MAIN ST AT 10:00 AM. CALLED SARAH AND JUSTIN AND ASKED THEM TO MEET ME THERE. JUSTIN CALLED TO CONFIRM HE WOULD MEET ME THERE. TCH * MET WITH MORRIS AND JUSTIN/VILLAGE, WALKED THROUGH BASEMENT, AND MOST THE FLOR AREAS AND VISITED A SELECT NUMBER OF ROOMS CHECKING FIRE FIRE VIOLATIONS. MORRIS TOOK NOTES AND WILL HANDLE VIOLATIONS NOT ALREADY ADDRESSED. TCH
23-8515 | CSD - Reinspection - Housing | 2023-03-02 | 2023-03-15 |  | Completed |  | * RI - (CI) APT #606 | * VIOLS SATISFIED TCH
23-13543 | CSD - Rental Property Complaint Inspection | 2023-03-13 | 2023-03-15 |  | Completed |  | TODD WILSON FROM UNIT 209 CALLED IN 571-842-3838 NO HOT WATER IN HIS BATHROOM SINCE NOVEMBER | * FORWARDED COMPLAINT TO SARAH WHO STATED SHE WAS UNAWARE OF VIOLATION. TOLD HER IF SHE WOULD LOOK INTO COMPLAINT FIIRST THING I WILL HOLD OFF CALLING TENANT TILL TUESDAY AFTERNOON IN HOPES THE VIOLATION CAN BE HANDLED. TCH * 3-14-23 CALLED TENANT @ 2:16 PM - UNABLE TO LEAVE MESSAGE. TCH * 3-15-23 CALLED THE TENANT @ 7:57 AM - UNABLE TO LEAVE MESSAGE, MAILBOX WAS FULL. CALLED SARAH TO INQUIRE ABOUT THE RETURN OF HOT WATER IN THE BATHROOM - CALL WAS DISCONNECTED. TCH @ 11:24 AM - TALKED WITH MGR SARAH TAYLOR - HAS RECVD CALLS FROM TENANT IN PAST FOR SAME REASON BUT NEVER A FOUNDED COMPLAINT, SAID IF TENANT CALLS BACK SHE MAKE VISIT WITH ME. TCH @ 1:01 PM TENANT HASN'T RETURNED MY PHONE CALLS - CANCELLING COMPLAINT. TCH
23-15176 | CSD - Rental Property Complaint Inspection | 2023-03-21 | 2023-03-22 | 2023-03-28 08:21 | Completed |  | * Apt #604 - TENANT JAZMAINE (331-422-9934) STATES NO HEAT. | * KNOCKED ON DOOR 9:45 AM - NO ANSWER. PHONE CALL, NO ANSWER. TCH * @ 10:10 AM - NO SHOW FROM TENANT. TCH * 3-27-23 RECVD CALL FROM JUSTIN/VILLAGE - HEAT RETURNED TO UNIT AFTER RESETING BREAKER. TCH
23-15767 | Environmental Clean Up |  | 2023-03-24 |  | Completed |  | ***24 HOUR NOTICE POSTED 3/23/23 1:10PM*** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, WOOD PIECES, PLASTIC BAGS, BOTTLES, CANS, AND ALL OTHER DEBRIS AT DUMPSTER SITE COMPLETED 3/24/23 1:24 KA
23-16210 | Environmental Clean Up | 2023-03-27 | 2023-03-27 |  | Completed |  | * NUISANCE PROPERTY CLEAN UP - LOOSE TRASH AND DEBRIS, INDOOR FURNITURE, CARDBOARD BOXES, TRASH BAGS AROUND DUMPSTER Cleaned up 3/27/23 12:24pm CJ MP | * CALLED BOJO WITH HEADS UP. TCH
23-14981 | CSD - Rental Property Complaint Inspection | 2023-03-21 | 2023-03-28 | 2023-03-28 08:33 | Completed |  | MICHAEL BREEDEN CALLED IN FROM UNIT 603 563-313-9934 STATING HE HAS NOT HAD HEAT FOR LAST 16 MONTHS. ALL MGMT GAVE HIM WAS ONE SMALL SPACE HEATER. HE DID FILE COMPLAINT IN 2021 BUT IT WAS CLOSED DUE TO NO CONTACT. . HIS LEASE IS STILL ACTIVE AND HE STILL HAS KEYS TO UNIT BUT IS NOW STAYING SOMEWHERE ELSE DUE TO THESE ISSUES. | * 3-21-23 @ 8:08 AM - CALLED TENANT - LM FOR HIM TO CALL BACK. TCH * 3-21-23 per Sarah Taylor's email: From: Village Property <villagepropertymanagementadm@gmail.com> Date: Tue, Mar 21, 2023 at 7:42 AM Subject: Re: FW: [EXT] New Task Assignment To: Haut, Tony <Tony.Haut@davenportiowa.com> Lol! He has mental health issues. He moved out months ago. I even have a letter from his worker stating he moved. I will forward it to you if I can find it. We literally already did a walkthrough of his unit and all like two months ago. * EMAIL DATED FROM 12- 29-22: This is a formal request on behalf of The Salvation Army GPD-TIP Program to request a 30-day notice of termination of the lease agreement regarding the rental property 324 Main Street APT 603 Davenport IA. The Salvation Army GPD-TIP Program is requesting the lease ending effective date to be 1/31/2023 due to communication with the occupant, Michael Breeden and his GPD-TIP Case Manager, and his acceptance into the Dept of VA’s HUD-VASH program. The Veteran and his Case Manager will be reaching out to you to schedule a time to turn over apartment keys. Amber Darrow The Salvation Army GPD Transition in Place Program Manager 309-256-5957 * 3-24-23 - APARTMENT APPEARS TO BE VACANT - NOT ENFORCING HEAT COMPLAINT. TCH
23-17003 | Environmental Clean Up | 2023-03-30 | 2023-03-30 |  | Completed |  | **NUISANCE PROPERTY IMMEDIATE CLEAN UP 3/30/23 ATA** PLEASE REMOVE AND PROPERLY DISPOSE OF RECLINE CHAIR, CLOTHING, AND WOOD PIECES AROUND DUMPSTER PU 3/30/23 2:35 KA
23-17560 | Environmental Clean Up |  | 2023-04-04 |  | Completed |  | **NUISANCE PROPERTY. IMMEDIATE CLEAN UP POSTED 4/3/23** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, INDOOR FURNITURE, CARPET, BOTTLES, CANS, CRATES, AND ALL OTHER DEBRIS AROUND DUMPSTER Cleaned up 4/4/23 7:55am CJ
23-17504 | CSD - Rental Property Complaint Inspection | 2023-04-03 | 2023-04-04 | 2023-04-26 10:30 | Completed | NSD 04 - Complaint Notice and Order | TODD WILSON FROM #209 CALLED IN NO HOT WATER SINCE NOVEMBER 571-842-3838 | * 4-3-23 @ 11:45 am - tried calling tenant - unable to leave message/mailbox full. Talked to Sarah, she is to place a 24 hr notice to make entry for/ inspection. TCH * @ 3:00 PM - CALLED TENANT - UNABLE TO LEAVE MESSAGE DUE TO MAILBOX BEING FULL. TCH * 4-4-23 @ 11:15 AM - WAS ABLE TO TALK TO TODD WHO AGREED TO MEET TODAY AT 1:00 PM. TCH * 4-4-23 @ 1:00 PM - HOT WATER WORKS FINE. (SHOWER WAS THE ISSUE) - BAD CANISTER IN SHOWER FAUSET + OTHER VIOLS. COMPLAINT LTR SENT REG MAIL & EMAILED. TCH
23-17853 | CSD - Rental Property Complaint Inspection | 2023-04-04 | 2023-04-05 | 2023-04-26 10:45 | Completed | NSD 04 - Complaint Notice and Order | NICK ROBINSON FROM APT 517 CALLED IN STATING NO HEAT SINCE HE MOVED IN BACK IN DECEMBER. MGMT STATING NOT GOING TO FIX IT NOW SINCE IT WILL BE SUMMER 309-236-9537 | * 4-4-23 DEALING WITH SERIES OF EMAILS ABOUT HEAT SUPPLY WITH SARAH/VILLAGE. TCH * 4-4-23 PER STAFF THAT HEATING UNIT IN APT UNREPAIRABLE. MUTIPLE STORIES OF WHY HEAT HASN'T BEEN RESTORED BY SARAH. TENANT JUST WANT HEAT BUT DOESN'T WANT TO MOVE - LIBBY PLANNING MEETING WITH TENANT TO WORK OUT A RESOLUTION. COMPLAINT LTR MAILED AND EMAILED TO MGR AND DH. TCH
23-18890 | Environmental Clean Up | 2023-04-10 | 2023-04-10 |  | Completed |  | **NUISANCE - IMMEDIATE CLEAN UP POSTED 4/10/23 9:05** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, PLASTIC BAGS, BOTTLES, CLOTHING, AND ALL OTHER DEBRIS AROUND DUMPSTER SITE picked up 4/10/23 11:39 MP/EB
23-11737 | CSD - Reinspection - Housing | 2023-03-03 | 2023-04-17 |  | Completed |  | * RI - FIRE SAFETY VIOLATION (LC LAST) | * 3-6-23 RETURNED LIBBY'S PHONE CALL ABOUT QUESTIONS - LM FOR HER TO CALL BACK. TCH * @ 11:23 AM - LIBBY CALLED BACK AND ASKED QUESTIONS ABOUT FIRE DOORS. TCH * 4-3-23 FIRE VIOL RE-INSPECTION WITH MORRIS. MODERATE AMOUNT OF REPAIR NOTED. ADDITIONAL RI SCHEDULED PER MORRIS ON 4-11-23 AT 9:30 AM. TCH * 4-17-23 PER JIM MORRIS - ALL FIRE VIOLATIONS SATISFIED. TCH
23-21000 | Environmental Clean Up | 2023-04-18 | 2023-04-18 |  | Completed |  | **NUISANCE PROPERTY IMMEDIATE CLEAN UP 4/18/23** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, BINS, PALLETS, AND ALL OTHER DEBRIS AROUND DUMPSTER Complete 4/18/23 TH KG JS AB 6:33
23-22400 | Environmental Clean Up | 2023-04-25 | 2023-04-25 |  | Completed |  | **IMMEDIATE CLEAN UP NUISANCE PROPERTY** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, MATTRESSES, PLASTIC BAGS, CARTONS, AND ALL OTHER DEBRIS SURROUNDING DUMPSTER picked up 4/25/23 8:07 MP/KG
23-18104 | CSD - Reinspection - Housing | 2023-04-04 | 2023-04-26 | 2023-05-03 13:00 | Completed | NSD 29-Final Official Notice - 2nd Reinspection | * RI - CI APT #209 | * 4-26-23 TWO MINOR VIOLS NOT DONE BUT ADDING A HEAT VIOLATION TO FIINAL. HEAT TURNED ON AND AFTER 10 MINUTES SHUTS OFF. TEMP IN ROOM SET AT 78 DEG BUT TEMP GOT TO 65 DEG BEFORE SHUTTING ITSELF OFF. SENDING 7 DAY FINAL LETTER. LTR SENT REG MAIL TO PO BOX WITH COPY TO TENANT + EMAILED. TCH
23-18232 | CSD - Reinspection - Housing | 2023-04-05 | 2023-04-26 | 2023-05-26 | Completed | NSD 15 - Notice to Vacate | * RI - COMPLAINT IN APT #517 | * 4-25-23 EMAIL FROM SARAH/VILLAGE; Tony, The system over at Davenport has been switched over for the season, so do you still want to do the inspection tomorrow when there is no real way to verify it working vs not working? Just let me know what you'd like for me to do. Thank you, Sarah. * 4-26-23 MY RESPONSE; As we discussed, the heating season is from Sept 15th through May 15th as per city code. I’ll be at the property at 10:30 am. I CALLED THE NICK/TENANT AND CONFIRMED VILLAGE DID NOT REPAIR HEAT. NICK STATED HE HAS FOUND A NEW PLACE AND WILL BE LEAVING NEXT WEEK. TAGGING 30 DAY - APT FOR NO HEAT. MAILED TO PO BOX REG/CERT MAIL + POSTED ON DOOR.TCH
23-23767 | Environmental Clean Up | 2023-05-01 | 2023-05-01 |  | Completed |  | **IMMEDIATE CLEAN UP. NUISANCE PROPERTY** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, CARPET, PLASTIV BINS, BOTTLES, CANS, AND ALL OTHER DEBRIS AROUND DUMPSTER SITE AS WELL AS REMOVE THE TOP PORTION OF DEBRIS FROM DUMPSTER SO LIDS CLOSE. COMPLETE CH 5/1/23 1:52 | COMPLAINT: The dumpster behind the Davenport Lofts owned by Andrew Wold is overflowing. Trash is blowing down the alley onto Main St. This continues to be a weekly issue with the property and its lack of management and responsibility. Debris complaint changed to immediate since Nuisance property 5/1/23 ATA
23-24316 | Environmental Clean Up |  | 2023-05-03 |  | Completed |  | **IMMEDIATE CLEAN UP - NUISANCE PROPERTY** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, INDOOR FURNITURE, AND ALL OTHER DEBRIS AROUND DUMPSTER SITE AS WELL AS TOP LAYER OF DUMPSTER SO LIDS MAY CLOSE COMPLETE CH 5/3/23 1:37
23-24573 | Environmental Clean Up |  | 2023-05-04 |  | Completed |  | **IMMEDIATE CLEAN UP - NUISANCE PROPERTY** PLEASE REMOVED AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, AND ALL OTHER DEBRIS AROUND DUMPSTER SITE AS WELL AS THE TOP LAYER TO WHERE LIDS CLOSE COMPLETE CH 5/4/23 10:47
23-25000 | Environmental Clean Up |  | 2023-05-08 |  | Completed |  | **IMMEDIATE CLEAN UP. NUISANCE PROPERTY** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, AND ALL OTHER DEBRIS AROUND DUMPSTER SITE TO INCLUDE TOP PORTION OF DUMPSTER SO LIDS CLOSE. P/U CH 5/8/23 10:19
23-22959 | CSD - Reinspection - Housing | 2023-04-26 | 2023-05-08 | 2023-06-03 07:30 | Completed | NSD 15 - Notice to Vacate | * FINAL RI - APT #209 | * 4-26-23 APARTMENT MAY BE VACATED PER CONVERSATION WITH LIBBY, SHE SAID VILLAGE WAS LETTING HIM OUT OF THE LAST TWO MONTHS OF HIS LEASE TO MOVE OUT. CALL LIBBY (563-549-1142) AND TENANT BEFORE MAKING VISIT. TCH NO WORK HAS BEEN DONE AND OWNER WAS NOT LETTING HIM OUT OF LEASE. 5-3-23 BBR 30 DAY VACATE SENT REG/CERT AND POSTED. 5-3-23 BBR
23-25503 | Environmental Clean Up |  | 2023-05-09 |  | Completed |  | **IMMEDIATE CLEAN UP. NUISANCE PROPERTY** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, AND ALL OTHER DEBRIS AROUND DUMPSTER SITE/ALLEY COMPLETE CH 5/9/23 11:48
23-9778 | BUILDING PERMIT | 2023-02-23 | 2023-05-12 |  | Completed |  | STRUCTURAL MASONRY REPAIRS TO WEST ELEVATION AS SPECIFIED IN ENGINEERS REPORT BY IA P.E. D. VALLIERE #22444 ALL PER CITY CODE.
23-10887 | BUILDING PERMIT | 2023-03-02 | 2023-05-12 |  | Completed |  | PERMIT FOR NEW WALL MOUNTED SIGN FOR ENVIED VINTAGE CLOTHING. SIGN APPROVED AND TO BE INSTALLED PER ZONING APPROVAL FOR SIZE AND SETBACKS.
23-25205 | CSD - Rental Property Complaint Inspection | 2023-05-15 | 2023-05-15 |  | Completed |  | UNIT 311 TRENT FUESSEL 563-940-3090. TRENT'S APARTMENT IS THE BACKSIDE WHERE BRICK WALL WAS WORKED ON. TRENT SAYS HIS WALLS ARE GETTING WORSE WITH CRACKS. | * CALLED AND TALKED TO TRENT/TENANT - OFFICE IS ALLOWING HIM TO BREAK LEASE AND MOVE EARLY. CANCELLED COMPLAINT. TCH
23-26855 | Environmental Clean Up | 2023-05-15 | 2023-05-15 |  | Completed |  | **NUISANCE PROPERTY IMMEDIATE CLEAN UP** PLEASE REMOVE AND PROPERLY DISPOSE OF ALL TRASH, LITTER, CARDBOARD, PLASTIC BAGS, BOTTLES, CANS, PAPER, AND ALL OTHER DEBRIS AROUND DUMPSTER, ALLEY, AND BLOWING THROUGH LOT OWNER COMPLIED CH 5/15/23 1:02
22-62762 | PLUMBING PERMIT |  |  |  | Planned |  | Install a lavatory, water closet, trim bathtub faucet, and install the kitchen sink
22-2967 | PLUMBING PERMIT |  |  |  | Planned
22-2964 | BUILDING PERMIT |  |  |  | Planned |  | REMODEL OF TWO EXISTING SPACES INTO (2) NEW APARTMENTS ON FIRST FLOOR. FIRE RATED WOOD OR STEEL STUD NON - BEARING INTERIOR WALLS. SPRINKLER SYSTEM TO BE UPDATED PER CODE & FIRE MARSHAL APPROVAL. ALL WORK SUBJECT TO ONSITE INSPECTION & APPROVAL . OTHER TRADES REQUIRE SEPARATE PERMITS. OTHER TRADES REQUIRE SEPARATE PERMITS. SMOKE AND CARBON MONOXIDE DETECTORS REQUIRED PER CODE. ALL PER CITY CODE.
22-2966 | MECHANICAL PERMIT |  |  |  | Planned
22-2965 | ELECTRICAL PERMIT |  |  |  | Planned
20-83090 | BUILDING PERMIT | 2020-12-17 |  |  | In Progress |  | REPAIR EAST, NORTH & SOUTH SIDES OF BRICK FACADE PER ENGINEER CHRIS TOWNSEND'S REPORT. ALL PER CITY CODE.
21-106818 | BUILDING PERMIT | 2021-12-15 |  |  | In Progress |  | ADD STEEL STUD WALLS IN EACH UNIT (211, 306, 406) WITH CLOSET. ELECTRICAL UPDATES TO EACH UNIT. OTHER TRADES REQUIRE SEPARATE PERMITS. SMOKE AND CARBON MONOXIDE DETECTORS REQUIRED PER CODE. ALL PER CITY CODE.
22-4842 | ELECTRICAL PERMIT | 2022-01-27 |  |  | In Progress |  | ADD GFCI RECEPTACLES, SWITCHES, SMOKE AND CARBON MONOXIDE DETECTORS.
23-5283 | CSD - Rental Certification Inspections | 2023-01-30 |  |  | Planned
23-6454 | CSD - Nuisance Abate/Inspect | 2023-02-04 |  |  | In Progress |  | * CALL FROM MID-AMERICAN ON CONDITION OF SOUTHWEST EXTERIOR BRICK WALL. | * 2-3-23 COMPLAINT FROM MID-AMERICAN FOR UNSAFE/DETERIORATED WALL. AT WEST-SOUTH WEST CORNER OF BUILDING. OSWALD, PRADHAN, MORRIS, ALD DUNN, ALD CONDON, MGR SARAH AND MYSELF IN ATTENDENCE. VISABLE DILAPIDATION OF VERTICLE BRICK WALL ON EXTERIOR AND INTERIOR WALLS. TRISHNA HAS BEEN WORKING WITH OWNER ANDREW WOLD, RUBEN GUZMAN AND STRUCTURAL ENGINEER ON REPAIRS. LETTERS AND PICTURES ATTACHED. GAS REGULATORS AND PIPING ON WEST EXTERIOR TO BE SHIELED WITH SCAFFOLDING BEFORE MI-AMER WILL WORK IN AREA. * 2-9-23 at 3:00 AM - TRISHNA AND I MET WITH OWNERS OF R.A. MASONERY - DISCUSSED THE WORK TO BE DONE AND SHORING OF THE CELLAR AND 1ST FLOOR WEST-SOUTHWEST INTERIOR/EXTERIOR WALLS WHICH HAD NOT BEEN STARTED THOUGH SUPPORT POST WERE PRESENT BUT NOT INSTALLED. DOCUMENTED NOTICED BRICK MOVEMENT IN EXTERIOR WALL WITH PICTURE ATTACHMENTS. WILL VISIT 2-10-23 AT 12:00 PM. TCH * 2-10-23 OBSERVED TEMP SHORING OF INTERIOR WALLS/SOUTHWEST WALLIN CELLAR AND 1ST FLOOR MAINT ROOM. EXTERIOR WALL NOT SHORED AS OF YET. RECIEVED PHONE MESSAGE FROM TRISHNA STATING MARK WITH BI-STATE MASONARY IS TAKING OVER REPAIRS OF THE ON WEST WALL. FOLLOW UP PICTURES ATTACHED. TCH * 2-13-23 ADDED NEW PICS TO TASK. TCH * 2-15-23 VISIT FOUND SCAFFOLDING INSTALLED AT EXTERIOR WEST WALL AND NOTHING DONE IN BASEMENT. TCH * 2-16-17 @ 11:00 AM TRISHNA AND I VISITED THE INTERIOR MMAINT ROOM - SCAFFOLDING BEING SET UP IN ROOM AND NO WORK ON WALL HAS BEGUN. TCH * 2-28-23 STOPPED BY TO CHECK PROGRESS, APPEARS THAT THE WEST WALL HAS COLLAPED INTO THE SCAFFOLDING. WORKERS STATED IT'S GOING TO BE A BIGGER JOB THAT WHAT THEY BELIEVED IT TO BE. TCH * 3-3-23 PER TRISHNA, A $50G CHANGE UP ORDER WAS PRESENTED BY BI-STATE FOR UNFORSEEN WORK NEEDING PREFORMED. ALL WORK STOPPED, BI-STATE NO LONGER WORKING ON BUILDING. TCH
23-25196 | CSD - Reinspection - Other | 2023-05-15 |  |  | In Progress |  | * UNIT 209 * REINSPECT ON 30 DAY VACATE
23-30329 | BUILDING PERMIT | 2023-05-24 |  |  | In Progress |  | REPLACE IN KIND 100 LINEAR FEET OF BRICK EXTERIOR ALL PER CITY CODE.
23-31222 | BUILDING PERMIT | 2023-05-30 |  |  | Planned |  | DUE TO LARGE BUILDING FAILURE/ COLLAPSE AND EXISTING STRUCTURE INSTABILITY- EMERGENCY DEMO OF ENTIRE BUILDING PER NOTICE AND ORDER ISSUED 5/29/23 BY ORDER OF DFD AND ON SITE VISUAL ENGINEERS REPORTING. DEMOLISH BUILDING AS PER CITY CODE. BACKFILL INSPECTION REQUIRED. ALL ACCESSORY STRUCTURES ARE TO BE REMOVED PER TITLE 17 OF THE CITY OF DAVENPORT MUNICIPAL CODE.